## RAID Log
RAID Log |  | Last updated: | 2019-06-30
Track major project risks, assumptions, issues and dependencies
No. | Category | Description | Priority | Next actions | Owner | Last update
1 | Risk | Resource bottlenecks due to team members being assigned to parallel projects | Medium | 1. Closely monitor progress of parallel projects. 2. Look for suitable external contractor who can support during peak phases. | John Smith | 2019-06-30
2 | Risk | Software does not fulfil customer requirements | High | 1. Create a prototype the customer can review 2. Create specification template to document customer needs | Patrick McGuinness | 2019-05-31
3 | Assumption | Office closed from Dec 20 - Jan 4 | Medium | no work during that time | Stella Sheets | 2019-05-31
4 | Assumption | Customer will take care of data extraction from current IT system | High | migrate address data | Frank Hudson | 2019-05-31
5 | Assumption | Customer will clean up current system data | High | migrate address data | Frank Hudson | 2019-05-31
6 | Issue | Current system interface does not support Windows 10 | Critical | reconciliation with software vendor | Jay Frank | 2019-05-31
7 | Dependency | Legal department to give approval before data migration | Critical | reconciliation with legal dept. | Stella Sheets | 2019-05-31

## Categories
Risk
Assumption
Issue
Dependency

## Priorities
Low
Medium
High
Critical